## Slide 1: White Concrete Company Code
Golden Block | Go-live to production (P): next steps
SNAGFREE and Golden Block | [ meeting date ]
Notes: Open by thanking the team for UAT effort. Purpose: agree the go-live date, the cutover plan and what each side does before go-live.

## Slide 2: Today we agree the go-live date and who does what
60 minutes
1
Where we are
DEV, Q and UAT status
2
UAT sign-off
What is left and when
3
Go-live timeline
Proposed date and milestones
4
Cutover plan
Six workstreams to production
5
What we need from you
Actions with owners and dates
6
Go/No-Go and support
Criteria and hypercare
7
Decisions and next steps
Confirm before we leave

## Slide 3: DEV and Q are complete; UAT is the last step
Six project phases since 19 July 2026
✓
Foundation
setup
✓
Core
configuration
✓
Data prep and
final config
✓
ZATCA and
master data
✓
Testing and
validation
6
User acceptance
(UAT)
In progress
Done
DEV configuration
All in-scope modules
Done
Q system testing
Integration and end-to-end
[ fill ]
UAT scenarios passed
Open defects: [ fill ]
Notes: Modules in scope: SD, FICO, MM, PP and QM, plus ZATCA e-invoicing for the new company code. Fill UAT pass count and open defects with the team before the meeting.

## Slide 4: UAT sign-off per module comes before cutover
Team to fill before the meeting
Module | Scenarios | Passed | Open defects | Blockers | Sign-off owner (GB) | Sign-off date
FICO | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ]
SD | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ]
MM | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ]
PP | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ]
QM | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ]
ZATCA e-invoicing | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ] | [ fill ]
Ask: signed UAT confirmation by email from each module owner by [ date ].

## Slide 5: Proposed timeline to go-live
T = go-live day. Proposed go-live: [ date ]
T-10
UAT signed off
[ dd Mon ]
T-5
Master data and user access ready
[ dd Mon ]
T-4
Transports imported to P
[ dd Mon ]
T-3
ZATCA production onboarding
[ dd Mon ]
T-2
Go/No-Go meeting
[ dd Mon ]
T
Go-live and first transactions
[ dd Mon ]
T+[ ]
Hypercare ends
[ dd Mon ]
Why a start-of-month date: the new company starts trading clean for its first period close and first VAT return.
Notes: Internal suggestion: Sunday 1 November 2026, first working day of the month in KSA. Confirm the trading start date of the legal entity first.

## Slide 6: Six workstreams take us to production
Each has one owner and a check before Go/No-Go
1
Transports
Customizing and software collections imported to P in the tested order
Owner: GB admin imports, SNAGFREE verifies
2
Production settings
Number ranges (incl. billing), posting periods, banks, cost centres, MRP
Owner: SNAGFREE
3
Master data
Extend materials, customers and suppliers; prices, BOMs, recipes
Owner: GB provides, [ owner ] loads
4
User access
Business roles extended to White Concrete org units
Owner: GB admin / IAM
5
ZATCA onboarding
Production CSID, eDocument and integration setup, invoice form
Owner: SNAGFREE + GB (Fatoora portal)
6
Go-live checks
First transaction in each cycle watched end to end
Owner: GB key users + SNAGFREE

## Slide 7: What we need from Golden Block
Dates agreed today go into the meeting minutes
# | Action | Owner | Due date
1 | Sign UAT per module | [ fill ] | [ fill ]
2 | Confirm White Concrete trading start date, VAT and CR numbers | [ fill ] | [ fill ]
3 | Name the admin and window to import collections into P | [ fill ] | [ fill ]
4 | Extend business roles and assign users for White Concrete | [ fill ] | [ fill ]
5 | Deliver final master data files (products, partners, prices, BOMs, recipes, inspection plans) | [ fill ] | [ fill ]
6 | Generate OTP on the Fatoora portal for ZATCA onboarding | [ fill ] | [ fill ]
7 | Provide house bank and bank account details | [ fill ] | [ fill ]
8 | Decide on opening balances (GL, assets, open items, stock) | [ fill ] | [ fill ]
9 | Name key users available on go-live day | [ fill ] | [ fill ]
10 | Agree White Concrete billing number format (own range per company code) | [ fill ] | [ fill ]
Notes: Contract: customer provides master data, key users, system access and licences; delays here move the schedule. In Public Edition, imports into P and business roles/users sit with Golden Block's administrator (contract excludes Basis and authorisations).

## Slide 8: ZATCA e-invoicing goes live in five steps
Invoices for the new company cannot be issued until step 4 is done
1
Confirm entity details
VAT, CR, address in the system
GB confirms
2
Production settings
eDocument and integration setup for White Concrete
SNAGFREE
3
Generate OTP
On the Fatoora portal
GB
4
Production CSID
Compliance checks pass; certificate issued
SNAGFREE + GB
5
First invoice
Cleared or reported; status checked
GB + SNAGFREE
To agree: what counts as successful ZATCA testing (passing in Q, or first invoice cleared from P).
Notes: Contract: 10% milestone is invoiced after successful ZATCA integration testing; the term is not defined, so agree it here. QR code changes are out of scope.

## Slide 9: Who does what at go-live
R = does the work A = accountable C = consulted I = informed
Activity | SNAGFREE | GB business | GB admin / IAM
UAT sign-off | C | A/R | I
Cutover plan | A/R | C | C
Import collections into P | C (verify) | I | A/R
Settings maintained in P | A/R | I | C
Master data files | C (templates) | A/R | I
Master data load | [ ] | [ ] | I
Business roles and users | I | C | A/R
ZATCA eDocument and integration | A/R | I | C
Fatoora OTP and CSID | R (support) | A/R | C
Go/No-Go decision | R (recommend) | A | C
Hypercare | A/R | R (report) | C

## Slide 10: We go live only when all nine criteria are met
Go/No-Go meeting at T-2: [ date ]
✓
UAT signed off
Signed email per module
✓
No open blockers
Agreed defect list
✓
Transports imported to P
Import logs clean
✓
P settings done
Incl. billing number range
✓
Master data loaded
Counts signed by GB
✓
Users can log in
Key-user access test
✓
ZATCA live
Production CSID active
✓
Opening balances agreed
In the minutes
✓
Support team named
Contact list issued
Notes: If No-Go: White Concrete does not post in P and the date moves. No technical rollback is needed for the existing company.

## Slide 11: Support after go-live
Remote hypercare while the first transactions and close run
Hypercare model
Duration | [ ] weeks from go-live
Hours | [ ]
Channel | [ email / ticket / group ]
Daily call | 15 minutes, issues and priorities
First month-end | [ included / not included ]
Issue log | Shared; severity, owner, status
Scope reminders
Hypercare fixes issues in the delivered scope
New requests are logged as change requests
Support is remote
Not included: intercompany, STO, new document types, new master records, print layouts beyond the ZATCA invoice form
Notes: Hypercare is not defined in the contract. Fill this slide only with what was agreed internally today.

## Slide 12: Your request: transactions dated from June 2026
Two options for White Concrete history; details after a test in Q
Option 1 (recommended)
Opening balances + monthly summaries
Balances, open items, stock and assets loaded at the go-live cut-off
One summary journal entry upload per month, June to September
Monthly P&L and balance sheet from June
No backdated invoices sent to ZATCA
Option 2 (change request)
Full replay of operations
Every purchase, production, sales and quality document re-entered
Month by month: inventory only posts in current and previous period
Month-end costing and close for each month
ZATCA and VAT impact if invoices were already issued
To decide: why the history is needed, and whether White Concrete already traded and invoiced since June.
Notes: Internal: Option 2 is outside the contract (data migration beyond scope; requests after UAT) and needs a CR with effort and timeline. Before offering it, test one June goods receipt, production order and invoice in Q. Migration cockpit loads open items and balances, not closed historical documents.

## Slide 13: Decisions today and next steps
Decisions needed today
UAT sign-off date
Go-live date and cutover window
Go/No-Go meeting date
Owner and date for each action
Opening balance approach
ZATCA success definition
Hypercare length and channel
Answer on postings since June
Next steps
Today
Minutes with decisions and actions
[ date ]
UAT sign-off received
[ date ]
Master data and access ready
[ date ]
Transports and ZATCA in P
[ date ]
Go/No-Go meeting
[ date ]
Go-live