## Cutover plan
Activities | Owner | Description | Planned date | Status
Agree on go-live date | Golden Block & SNAGFREE | Go-live Sunday 1 Nov 2026 | 2026-10-25 | Done
Agree on cutover date | Golden Block & SNAGFREE | Cutover / migration key date: Saturday 31 Oct 2026 Opening position = close of 31 Oct | 2026-10-25 | Done
Agree on opening balance approach | Golden Block & SNAGFREE | Opening balances at 31 Oct 2026, no backlog entry (confirmed) To decide: year-to-date P&L at 31 Oct; monthly history May-Sep (optional) | 2026-10-27 | In progress
UAT sign off | Golden Block | Golden Block to send signed UAT confirmation (email) on test environment (Q) | 2026-10-26 | Not started
Transport requests | SNAGFREE | Release customizing transports & software collections from DEV Import to PRD in tested order (Import Collection app); check import logs | 2026-10-27 | Not started
PRD settings (not transported) | SNAGFREE | Posting periods: October & November open Number ranges incl. White Concrete billing range Exchange rates at 31 Oct Migration key date 31.10.2026, status 'Ongoing' (Define Settings for Legacy Data Transfer) Asset transfer date 31.10.2026 | 2026-10-28 | Not started
Authorization handling & maintenance | Golden Block | Assign required business roles to users, restricted to White Concrete org units Assign data migration roles to upload users Key users test login in PRD | 2026-10-28 | Not started
Providing MM master data | Golden Block | Material master data for new plant will be provided by Golden Block (plant, storage locations, sales org, valuation, MRP, QM views) | 2026-10-26 | Not started
Upload MM master data | SNAGFREE | Material master data (data provided by Golden Block) Product - extend existing record by new org levels Batches (if batch managed), info records, source lists | 2026-10-27 | Not started
Upload FICO master data | SNAGFREE | Upload GL account master data using a copy from PRD (extend to White Concrete) | 2026-10-27 | Not started
Upload FICO master data | Golden Block | Business partners (FI customers & suppliers - company code data) Fixed assets (master records) Bank accounts Cost centers Profit centers Activity types | 2026-10-28 | Not started
Upload SD master data | Golden Block | Business partners data (customers) - sales area Conditions (pricing) Credit limit if needed | 2026-10-28 | Not started
Upload PP master data | SNAGFREE | Prepare & upload validated master data BOM, resources (work centers), master recipes, production versions QM inspection plans & master inspection characteristics | 2026-10-28 | Not started
Validate PP master data | Golden Block | Validate master data extract from PRD (BOM, resources (work centers), master recipe, QM master data) | 2026-10-29 | Not started
Activity rates & standard cost release | SNAGFREE | Plan activity rates for new plant Run & release standard cost estimates Must be done before stock upload | 2026-10-29 | Not started
Prepare opening balance templates | Golden Block | Fill migration templates: stock, open POs, open SOs, AR & AP open items (legal invoice numbers), fixed asset values, GL balances (excluding stock, AR, AP and asset accounts) | 2026-10-27 | Not started
Test upload of opening balances (Q) | SNAGFREE | Test load of all opening balance templates in test environment (Q) Reconcile and report errors back to Golden Block | 2026-10-28 | Not started
Close open process orders & inspection lots | Golden Block | Finish or close open process orders in current process Usage decision on open inspection lots before cut-off | 2026-10-29 | Not started
Cutover: stop transactions & stock count | Golden Block | End of 31 Oct: stop transacting in current system Physical stock count per plant / storage location / batch Snapshot of open POs, open SOs, AR and AP | 2026-10-31 | Not started
Upload stock & open orders | SNAGFREE | Material inventory balance (mvt 561) at 31.10.2026 (data from Golden Block) Open purchase orders, open sales orders Must be loaded before users start on 1 Nov | 2026-10-31 | Not started
Upload AR & AP open items | SNAGFREE | FI - Accounts receivable open item, FI - Accounts payable open item Key date 31.10.2026, legal invoice numbers | 2026-11-01 | Not started
Go live | Golden Block & SNAGFREE | Users start working First transaction per cycle checked end to end | 2026-11-01 | Not started
Close October in current system | Golden Block | Final October books and 31 Oct trial balance October VAT return prepared from current system | 2026-11-04 | Not started
Upload fixed asset values | SNAGFREE | Acquisition value & accumulated depreciation at 31.10.2026 | 2026-11-05 | Not started
Upload GL opening balances | SNAGFREE | FI - G/L account balance at 31.10.2026 (YTD P&L if agreed) Migration clearing accounts must net to zero | 2026-11-05 | Not started
Upload monthly history (optional) | SNAGFREE | FI - Historical balance May-Sep 2026, if agreed (reporting only) | 2026-11-08 | Not started
Maintain FICO & MM opening balances - sign off | Golden Block | Reconcile SAP trial balance, AR, AP, assets and stock to 31 Oct figures Golden Block finance sign-off | 2026-11-09 | Not started
Close data migration | SNAGFREE | Close migration (legacy data transfer settings) Close October posting periods | 2026-11-10 | Not started
PRD UAT sign off | Golden Block | Golden Block to confirm in writing that production (PRD) works after first transactions and opening balances are verified | 2026-11-10 | Not started
Legend
Golden Block |  | Edit the white cells: Planned date and Status (pick from the list).
SNAGFREE |  | Dates assume go-live Sunday 1 Nov 2026 and cutover Saturday 31 Oct 2026; KSA work week Sunday to Thursday.
Golden Block & SNAGFREE |  | Opening balances are loaded as at 31.10.2026. Stock, open orders and AR/AP before users start; GL and assets after October is closed.

## Data to upload
# | Data | Migration object / app (confirm name in PRD) | Type | Provided by | Uploaded by | Load by | Depends on
1 | G/L accounts extended to White Concrete | G/L account object or Manage G/L Account Master Data | Master data | SNAGFREE | SNAGFREE | 2026-10-27 | -
2 | Cost centers, profit centers, activity types | Cost center / Profit center / Activity type objects or apps | Master data | Golden Block | Golden Block | 2026-10-28 | G/L accounts
3 | Banks, house banks, bank accounts | Manage Banks / Manage Bank Accounts | Master data | Golden Block | Golden Block | 2026-10-28 | G/L accounts
4 | Customers extended to company code & sales area | Customer - extend existing record by new org levels | Master data | Golden Block | Golden Block | 2026-10-28 | -
5 | Suppliers extended to company code & purchasing org | Supplier - extend existing record by new org levels | Master data | Golden Block | Golden Block | 2026-10-28 | -
6 | Products extended to new plant | Product - extend existing record by new org levels | Master data | Golden Block | SNAGFREE | 2026-10-27 | -
7 | Batches (if batch managed) | Batch | Master data | Golden Block | SNAGFREE | 2026-10-28 | Products
8 | BOMs, resources, master recipes, production versions | PP migration objects | Master data | Golden Block | SNAGFREE | 2026-10-28 | Products
9 | Inspection plans, master inspection characteristics | QM migration objects | Master data | Golden Block | SNAGFREE | 2026-10-28 | Products
10 | Sales prices, credit limits | Condition records / Manage Prices - Sales; credit management | Master data | Golden Block | Golden Block | 2026-10-28 | Customers, products
11 | Info records, source lists | Purchasing info record / source list | Master data | Golden Block | SNAGFREE | 2026-10-28 | Suppliers, products
12 | Fixed asset master records | Fixed asset object | Master data | Golden Block | Golden Block | 2026-10-28 | Cost centers
13 | Activity rates & standard costs | Manage Cost Rates - Plan; costing run (release) | Master data | Golden Block | SNAGFREE | 2026-10-29 | BOMs, recipes, resources
14 | Stock (quantity & value) | Material inventory balance (mvt 561) | Opening balance | Golden Block | SNAGFREE | 2026-10-31 | Standard costs released
15 | Open purchase orders | Purchase order (only open PO) | Open item | Golden Block | SNAGFREE | 2026-10-31 | Suppliers, products
16 | Open sales orders | Sales order (only open SO) | Open item | Golden Block | SNAGFREE | 2026-10-31 | Customers, prices
17 | Customer open items | FI - Accounts receivable open item | Open item | Golden Block | SNAGFREE | 2026-11-01 | Customers, key date
18 | Supplier open items | FI - Accounts payable open item | Open item | Golden Block | SNAGFREE | 2026-11-01 | Suppliers, key date
19 | Fixed asset values | Fixed asset object (balances) | Opening balance | Golden Block | SNAGFREE | 2026-11-05 | Asset masters, transfer date
20 | GL balances (excl. stock, AR, AP, assets) | FI - G/L account balance and open/line item | Opening balance | Golden Block | SNAGFREE | 2026-11-05 | All loads above
21 | Monthly history May-Sep (optional) | FI - Historical balance | History | Golden Block | SNAGFREE | 2026-11-08 | Key date, cost/profit centers