## Feasibility
Critical path (the chain that sets the date)
Step | Owner | Latest finish | Slack | If late
Transports released from DEV (1.2) |  | 2026-10-27 | None | Every PRD load slips one day
Transports imported into PRD (1.3) |  | 2026-10-28 | Half a day | Master data loads cannot start
Upload users have Migrate Your Data access (2.1) |  | 2026-10-27 | None | Nobody can load on Wed
Product list confirmed and template validated (3.9, 3.11) |  | 2026-10-28 | Half a day | Product extension, PP/QM data and costing all slip
Product extension loaded in PRD (3.12) |  | 2026-10-28 | Half a day | BOMs, recipes and costing slip to Fri/Sat
BOMs, resources, recipes, production versions (3.14-3.16) |  | 2026-10-29 | None | Costing cannot run
Standard costs released (3.24) |  | 2026-10-29 | Until Sat 12:00 | Stock cannot be valued; stock load fails
Roles assigned and key users tested (2.5, 2.6) |  | 2026-10-29 | None | Users cannot post on 1 Nov
Stock count and final templates (6.2-6.4) |  | 2026-10-31 | Until Sat evening | Stock, POs, SOs, AR, AP not loaded before users start
Conditions to hold 1 Nov (all by Wed 28 Oct 12:00)
Condition | Owner | Due | Status | Why
Transports imported into PRD without errors |  | 2026-10-28 | Open | Everything else is built on them
Upload users have Migrate Your Data access in PRD |  | 2026-10-27 | Open | Needed for every load
Product list confirmed and user-role matrix received |  | 2026-10-28 | Open | Starts the material and authorization chains
Bank details, cost / profit centres, customers and suppliers to extend received |  | 2026-10-28 | Open | Finance master data must be in before open items
Golden Block staff confirmed for Sat 31 Oct (stock count, finance, warehouse) and Sun 1 Nov |  | 2026-10-28 | Open | Cutover cannot run without them
Will more consultants help?
Area | Owner | Helps? | Effect on date | Why
Parallel loads: finance, materials, PP/QM, prices |  | Yes | Saves about half a day | Separate consultants can load these at the same time; one extra MM/PP consultant shortens the critical path
Test loads in Q and weekend loads / reconciliation |  | Yes | Reduces weekend risk | An extra consultant can test while others load in PRD
Authorization design support |  | Partly | Small | Can prepare role changes, but Golden Block's admin must save and assign them
Golden Block data, validation and approvals |  | No | None | Only Golden Block can confirm products, prices, balances and sign off
Transport import, user access |  | No | None | Golden Block admin task unless SNAGFREE is given the role
Stock count, closing October in the current system |  | No | None | Business activities on Golden Block's side
Fallback if No-Go on Thu 29 Oct
Option | Owner | Cutover | Go-live | Assessment
A. Next month start (recommended fallback) |  | 2026-11-30 | 2026-12-01 | Clean start of period for reporting and VAT; uses November to finish master data calmly
B. Mid-November |  | 2026-11-14 | 2026-11-15 | Workable, but November reporting and VAT are split between two systems
C. Use Fri 30 Oct as an extra working day |  | 2026-10-31 | 2026-11-01 | Keeps 1 Nov if only one day is lost; needs both teams to agree to work the weekend

## Go-No-Go
# | Criterion | Evidence | Owner | Status | Comment
1 | UAT signed off by every module | Signed email | Golden Block | Open
2 | All transports imported into PRD, no errors | Import logs | Golden Block | Open
3 | PRD settings done: key date, asset transfer date, periods, number ranges | Runbook rows 1.4-1.9 Done | SNAGFREE | Open
4 | Finance master data and business partner extensions loaded | Runbook 3.1-3.6 Done | Golden Block & SNAGFREE | Open
5 | Products extended to the new plant and spot-checked | Runbook 3.12-3.13 Done | Golden Block & SNAGFREE | Open
6 | PP/QM master data loaded and validated | Runbook 3.14-3.18 Done | Golden Block & SNAGFREE | Open
7 | Standard costs released, or release confirmed by Sat 12:00 | Costing run released | SNAGFREE | Open
8 | Opening balance templates passed the test load in Q | Runbook 4.4-4.5 Done | Golden Block & SNAGFREE | Open
9 | Roles assigned; every key user tested access | Runbook 2.6 Done | Golden Block | Open
10 | Golden Block staff confirmed for stock count and cutover weekend | Named list | Golden Block | Open
11 | No open blocker defects | Defect list | Golden Block & SNAGFREE | Open
Decision (Go / No-Go):
Decided by / date:

## Runbook
ID | Activity | Action steps | App / tool | Owner | Support | Date | Time | Depends on | Done when | Status | Comments
0. Mobilise (today)
0.1 | UAT sign-off on file | Golden Block sends signed UAT confirmation (FICO, MM, SD, PP, QM) by email | Email | Golden Block |  | 2026-10-27 | EOD | - | Signed email filed | In progress
0.2 | Name the cutover team | Golden Block: sponsor, finance lead, key user per module, system/IAM admin, warehouse lead for stock count SNAGFREE: cutover lead + FICO, MM/SD, PP/QM consultants Confirm who works Sat 31 Oct and Sun 1 Nov | Contact list | Golden Block & SNAGFREE |  | 2026-10-27 | EOD | - | Contact list sent to all | Not started
0.3 | Daily cutover calls | 15-minute call at 09:00 and 16:00 until go-live: status per row, blockers, decisions | Teams | SNAGFREE | Golden Block PM | 2026-10-27 | 16:00 | - | Calls in calendar | Not started
0.4 | Send data request with deadline | Send Golden Block the list of inputs due Wed 28 Oct 12:00: user-role matrix, bank details, cost/profit centres, customers & suppliers to extend, product list for new plant, prices, test snapshot of open POs/SOs/AR/AP | Email | SNAGFREE |  | 2026-10-27 | PM | - | Email sent | Not started
0.5 | Change freeze | No configuration changes for White Concrete in DEV except agreed fixes; every fix goes by transport | - | SNAGFREE |  | 2026-10-27 | PM | - | Freeze announced | Not started
1. Production system readiness (Tue 27 - Thu 29)
1.1 | Final transport list | List all customizing requests and software collections in the order imported to Q, incl. billing number range (flexible numbering), invoice form, output settings | Export Customizing Transports / Export Software Collection | SNAGFREE |  | 2026-10-27 | PM | - | List with import order | Not started
1.2 | Release transports from DEV | Release every request on the list; nothing left open in DEV | Export Customizing Transports | SNAGFREE |  | 2026-10-27 | EOD | 1.1 | All released | Not started
1.3 | Import transports into PRD | Import in the listed order; check every import log | Import Collection | Golden Block | SNAGFREE (verify) | 2026-10-28 | 09:00 | 1.2 | All imported, no errors | Not started
1.4 | Verify org structure in PRD | Company code, plant, storage locations, sales org / distribution channel / division, purchasing org, shipping points, controlling area assignment | Display apps / Configure Your Solution | SNAGFREE |  | 2026-10-28 | 11:00 | 1.3 | Checklist ticked | Not started
1.5 | Migration key date | Set 31.10.2026 with status 'Ongoing' for White Concrete | Define Settings for Legacy Data Transfer | SNAGFREE |  | 2026-10-28 | PM | 1.3 | Key date saved | Not started
1.6 | Asset transfer date | Set 31.10.2026 (not earlier than the G/L migration date) | Make Company Code Settings (Asset Accounting) | SNAGFREE |  | 2026-10-28 | PM | 1.5 | Date saved | Not started
1.7 | Posting periods | October and November open for White Concrete; check whether White Concrete shares a posting-period variant with company code 1000 | Manage Posting Periods | SNAGFREE | Golden Block finance | 2026-10-28 | PM | 1.3 | Periods open, variant checked | Not started
1.8 | Number ranges in PRD | Journal entries 2026 and 2027; billing range for White Concrete (flexible numbering) on every billing type in scope | Configure Your Solution | SNAGFREE |  | 2026-10-28 | PM | 1.3 | Ranges present | Not started
1.9 | Inventory period | Confirm current inventory period is October 2026 for White Concrete | Allow Posting to Previous Period | SNAGFREE |  | 2026-10-28 | PM | 1.3 | Period = 10/2026 | Not started
1.10 | Output and forms | PO, delivery and billing output determined for new org units; invoice form shows White Concrete details | Output Parameter Determination | SNAGFREE |  | 2026-10-29 | AM | 1.3 | Preview checked | Not started
1.11 | Approval workflows | PR/PO approval conditions cover White Concrete company code / plant | Manage Workflows for Purchase Requisitions / Purchase Orders | SNAGFREE | Golden Block procurement | 2026-10-29 | AM | 1.3 | Conditions saved | Not started
1.12 | Scheduled jobs | MRP run for new plant; inventory period close; other periodic jobs include White Concrete | Schedule MRP Runs / Application Jobs | SNAGFREE |  | 2026-10-29 | PM | 1.3 | Jobs scheduled | Not started
2. Authorizations (Tue 27 - Thu 29) - Golden Block admin
2.1 | Data migration access | Give upload users (SNAGFREE consultants, Golden Block uploaders) access to Migrate Your Data in PRD - needed before master data loads on Wed | Maintain Business Users | Golden Block |  | 2026-10-27 | EOD | - | Uploaders can open the app | Not started
2.2 | User-role matrix | List every White Concrete user and their job: finance, procurement, warehouse, production, quality, sales | Excel | Golden Block | SNAGFREE (template) | 2026-10-27 | EOD | - | Matrix received | Not started
2.3 | Role design decision | Per role: extend existing role restrictions (users working for both companies) or copy a role restricted to White Concrete only | - | Golden Block | SNAGFREE (advise) | 2026-10-28 | AM | 2.2 | Decision per role | Not started
2.4 | Maintain role restrictions | Add White Concrete values (company code, plant, sales org / DC / division, purchasing org, profit centre where used) to write and read restrictions | Maintain Business Roles | Golden Block |  | 2026-10-28 | EOD | 2.3, 1.3 | Roles saved | Not started
2.5 | Assign roles to users | Assign the business roles to each business user | Maintain Business Users | Golden Block |  | 2026-10-29 | AM | 2.4 | Users assigned | Not started
2.6 | Key-user access test | Each key user opens their apps for White Concrete in PRD (display only) and reports missing access; trace and fix gaps | Display Authorization Trace | Golden Block | SNAGFREE | 2026-10-29 | PM | 2.5 | All key users confirmed | Not started
2.7 | No-posting instruction | Tell users not to post for White Concrete in PRD until the go-live announcement | Email | Golden Block |  | 2026-10-29 | PM | 2.5 | Email sent | Not started
3a. Master data - Finance and business partners (Wed 28)
3.1 | G/L accounts | Extend G/L accounts to White Concrete using a copy of company code 1000 data in PRD; check reconciliation accounts, open-item management, tax category, field status | Manage G/L Account Master Data | SNAGFREE |  | 2026-10-28 | AM | 1.3 | All accounts extended | Not started
3.2 | Cost centres & profit centres | Create cost centres, profit centres and hierarchy nodes for White Concrete | Manage Cost Centers / Manage Profit Centers | Golden Block | SNAGFREE FICO | 2026-10-28 | PM | 1.3 | Created and checked | Not started
3.3 | Activity types | Create activity types and assign to production cost centres | Manage Activity Types | Golden Block | SNAGFREE CO | 2026-10-28 | PM | 3.2 | Created | Not started
3.4 | Banks and bank accounts | House banks and bank accounts with G/L accounts | Manage Banks / Manage Bank Accounts | Golden Block | SNAGFREE FICO | 2026-10-28 | PM | 3.1 | Accounts active | Not started
3.5 | Customers - extend | Company code data (reconciliation account, payment terms) and sales area data (pricing, shipping, tax classification, account assignment group) | Migrate Your Data: Customer - extend existing record by new org levels | Golden Block | SNAGFREE SD/FICO | 2026-10-28 | EOD | 3.1 | Extended, spot-checked | Not started
3.6 | Suppliers - extend | Company code data (reconciliation account, payment terms, payment methods, withholding tax) and purchasing org data | Migrate Your Data: Supplier - extend existing record by new org levels | Golden Block | SNAGFREE MM/FICO | 2026-10-28 | EOD | 3.1 | Extended, spot-checked | Not started
3.7 | Fixed asset master records | Asset masters with asset class, cost centre, capitalisation date (values come after go-live) | Migrate Your Data: Fixed asset | Golden Block | SNAGFREE FICO | 2026-10-29 | PM | 3.2 | Masters created | Not started
3b. Master data - Material extension from company code 1000 (Tue 27 - Wed 28) - CRITICAL PATH
3.8 | Extract products from PRD | Export products used by White Concrete with company code 1000 plant data as reference (raw materials, semi-finished, finished, packaging) | Manage Product Master Data (export) | SNAGFREE |  | 2026-10-27 | EOD | - | Extract sent to Golden Block | Not started
3.9 | Confirm product list | Golden Block confirms which products White Concrete needs and removes the rest | Excel | Golden Block |  | 2026-10-28 | 10:00 | 3.8 | List confirmed | Not started
3.10 | Map new org values | Fill template: new plant, storage locations, sales org / DC (sales views), valuation class, price control, moving price for V items, MRP views, work scheduling, QM inspection setup, White Concrete profit centre, tax classification | Migrate Your Data: Product - extend existing record by new org levels | SNAGFREE |  | 2026-10-28 | 11:00 | 3.9, 1.3 | Template complete | Not started
3.11 | Validate mapped template | Golden Block checks MRP settings, valuation class, price control and storage locations | Excel | Golden Block |  | 2026-10-28 | 12:30 | 3.10 | Written OK | Not started
3.12 | Load product extension | Simulate, fix errors, migrate in PRD | Migrate Your Data | SNAGFREE |  | 2026-10-28 | PM | 3.11, 2.1 | All products extended | Not started
3.13 | Spot check products | Golden Block MM key user checks 10 products: all views present for new plant and sales org | Manage Product Master Data | Golden Block |  | 2026-10-28 | EOD | 3.12 | 10 products OK | Not started
3c. Master data - Production, quality, prices (Thu 29)
3.14 | Resources / work centres | Create for new plant (copy from company code 1000 plant where same); cost centre and activity type assignment, formulas | Migrate Your Data / Manage Work Centers | SNAGFREE |  | 2026-10-29 | AM | 3.3, 3.12 | Created | Not started
3.15 | BOMs | Bills of material for new plant | Migrate Your Data: Bill of material | SNAGFREE |  | 2026-10-29 | AM | 3.12 | Created | Not started
3.16 | Master recipes & production versions | Master recipes and production versions for new plant | Migrate Your Data | SNAGFREE |  | 2026-10-29 | AM | 3.14, 3.15 | Created | Not started
3.17 | QM master data | Master inspection characteristics, inspection methods, inspection plans; inspection types active in product QM view | Migrate Your Data / QM apps | SNAGFREE |  | 2026-10-29 | AM | 3.12 | Created | Not started
3.18 | Validate PP/QM master data | Golden Block validates the PRD extract: BOMs, resources, master recipes, QM master data | Excel extract | Golden Block |  | 2026-10-29 | 12:00 | 3.14-3.17 | Written OK | Not started
3.19 | Purchasing info records & source lists | Purchase prices and sources for the new plant / purchasing org | Migrate Your Data | SNAGFREE | Golden Block (data) | 2026-10-29 | AM | 3.6, 3.12 | Created | Not started
3.20 | Sales prices & credit limits | Sales price conditions for the new sales org; credit limits if used | Manage Prices - Sales / credit management | Golden Block | SNAGFREE SD | 2026-10-29 | PM | 3.5, 3.12 | Prices active | Not started
3d. Costing - must finish before the stock load (Thu 29) - CRITICAL PATH
3.21 | Plan activity rates | Activity rates for new plant cost centres, October and November 2026 (rates from Golden Block finance) | Manage Cost Rates - Plan | SNAGFREE | Golden Block finance | 2026-10-29 | AM | 3.3 | Rates saved | Not started
3.22 | Run standard costing | Costing run for all White Concrete products; fix errors (missing prices, BOMs, recipes) | Costing run app | SNAGFREE |  | 2026-10-29 | PM | 3.16, 3.19, 3.21 | Run without errors | Not started
3.23 | Review standard costs | Golden Block finance reviews top items and approves | Costing run results | Golden Block |  | 2026-10-29 | PM | 3.22 | Written OK | Not started
3.24 | Mark & release standard costs | Release so the price is valid for the 31.10 stock load (latest Sat 31 Oct 12:00) | Costing run app | SNAGFREE |  | 2026-10-29 | EOD | 3.23 | Released | Not started
4. Opening balance preparation & test (Tue 27 - Thu 29)
4.1 | Final finance decisions | Year-to-date P&L at 31.10 (yes/no); monthly history May-Sep (yes/no); GR/IR and goods in transit; any balances with company code 1000 | Meeting | Golden Block & SNAGFREE |  | 2026-10-28 | AM | - | Decisions emailed | Not started
4.2 | Send migration templates | Download templates from Migrate Your Data: stock, open PO, open SO, AR open items, AP open items, fixed assets, G/L balances, historical balances | Migrate Your Data | SNAGFREE |  | 2026-10-27 | EOD | - | Templates sent | Not started
4.3 | Fill templates with test snapshot | Golden Block fills all templates with current figures as a test | Excel | Golden Block | SNAGFREE | 2026-10-28 | EOD | 4.2 | Templates returned | Not started
4.4 | Test load in Q | Simulate and migrate stock (561), open PO, open SO, AR, AP in Q; report errors | Migrate Your Data (Q) | SNAGFREE |  | 2026-10-29 | AM | 4.3 | Loads pass in Q | Not started
4.5 | Fix template errors | Correct data and format issues found in the test | Excel | Golden Block | SNAGFREE | 2026-10-29 | PM | 4.4 | Clean re-test | Not started
4.6 | Close open orders and lots | Finish or close open process orders in the current process; usage decision on open inspection lots | Current process | Golden Block |  | 2026-10-29 | EOD | - | None open | Not started
4.7 | Plan stock count | Count sheets per plant / storage location / batch; counting team and time on Sat 31 Oct | Count sheets | Golden Block |  | 2026-10-29 | EOD | - | Plan issued | Not started
5. Go / No-Go (Thu 29 Oct 17:00)
5.1 | Go / No-Go meeting | Review every criterion on the Go-No-Go sheet; record the decision by email | Meeting | Golden Block & SNAGFREE |  | 2026-10-29 | 17:00 | All rows above | Decision emailed | Not started
5.2 | If No-Go: fallback | Move cutover to Mon 30 Nov and go-live to Tue 1 Dec; inform users | Email | Golden Block | SNAGFREE | 2026-10-29 | 18:00 | 5.1 | Communicated | Not started
6. Cutover weekend (Sat 31 Oct - Sun 1 Nov 08:00)
6.1 | Stop transactions in current system | Last receipts, issues and invoices for White Concrete in the current system at the agreed cut-off time | Current system | Golden Block |  | 2026-10-31 | [time] | 5.1 | Cut-off confirmed | Not started
6.2 | Physical stock count | Count per plant / storage location / batch / stock type; signed count sheets | Count sheets | Golden Block |  | 2026-10-31 | PM | 6.1 | Sheets signed | Not started
6.3 | Final stock template | Quantities and values from the count, reconciled to the current system | Excel | Golden Block | SNAGFREE MM | 2026-10-31 | PM | 6.2 | Template final | Not started
6.4 | Final open items templates | Open POs, open SOs, AR and AP open items at cut-off (legal invoice numbers, due dates) | Excel | Golden Block | SNAGFREE | 2026-10-31 | PM | 6.1 | Templates final | Not started
6.5 | Exchange rates | Rates at 31.10.2026 for foreign-currency items | Currency Exchange Rates | SNAGFREE | Golden Block finance | 2026-10-31 | PM | - | Rates saved | Not started
6.6 | Load stock | Material inventory balance (mvt 561), key date 31.10.2026: simulate, migrate | Migrate Your Data | SNAGFREE |  | 2026-10-31 | Evening | 6.3, 3.24 | Loaded, no errors | Not started
6.7 | Load open POs and SOs | Purchase order (only open PO), Sales order (only open SO) | Migrate Your Data | SNAGFREE |  | 2026-10-31 | Evening | 6.4, 3.12 | Loaded | Not started
6.8 | Load AR and AP open items | FI - Accounts receivable open item, FI - Accounts payable open item, key date 31.10.2026 | Migrate Your Data | SNAGFREE |  | 2026-10-31 | Night | 6.4, 1.5 | Loaded | Not started
6.9 | Reconcile loads | Stock quantity and value vs count; PO/SO counts; AR/AP totals vs current system; migration clearing accounts | Stock / G/L apps | SNAGFREE | Golden Block finance | 2026-11-01 | 07:00 | 6.6-6.8 | Differences explained | Not started
6.10 | Sign off loaded data | Golden Block finance and warehouse confirm stock, AR, AP | Email | Golden Block |  | 2026-11-01 | 07:30 | 6.9 | Sign-off email | Not started
7. Go-live day 1 (Sun 1 Nov)
7.1 | Go-live announcement | Users may start posting for White Concrete in PRD | Email | Golden Block |  | 2026-11-01 | 08:00 | 6.10 | Email sent | Not started
7.2 | First transactions watched | PR > PO > GR > supplier invoice; sales order > delivery > billing (check billing number and form); process order > confirmation > GR; inspection lot > usage decision; incoming / outgoing payment | Business apps | Golden Block | SNAGFREE (all) | 2026-11-01 | Day | 7.1 | Each cycle passed once | Not started
7.3 | Check journal entries | G/L account, profit centre, cost centre and tax code on the first postings | Manage Journal Entries | SNAGFREE |  | 2026-11-01 | Day | 7.2 | Checked | Not started
7.4 | Issue log and support | Issue log open (date, user, module, severity, status); daily call during hypercare | Issue log | SNAGFREE | Golden Block key users | 2026-11-01 | Day | - | Log shared | Not started
8. After go-live (2 - 10 Nov)
8.1 | Close October in current system | Final October books and 31 Oct trial balance; October VAT return from current system | Current system | Golden Block |  | 2026-11-04 |  | - | Trial balance sent | Not started
8.2 | Load fixed asset values | Acquisition value and accumulated depreciation at 31.10.2026 | Migrate Your Data: Fixed asset | SNAGFREE |  | 2026-11-05 |  | 8.1, 3.7 | Loaded | Not started
8.3 | Load G/L balances | All balance-sheet accounts except stock, AR, AP and asset accounts; YTD P&L if agreed | Migrate Your Data: FI - G/L account balance | SNAGFREE |  | 2026-11-05 |  | 8.1 | Loaded | Not started
8.4 | Load monthly history (optional) | FI - Historical balance May-Sep 2026, if agreed | Migrate Your Data | SNAGFREE |  | 2026-11-08 |  | 8.1 | Loaded | Not started
8.5 | Full reconciliation | Trial balance, AR, AP, assets, stock vs 31 Oct; migration clearing accounts net to zero | Trial balance apps | SNAGFREE | Golden Block finance | 2026-11-09 |  | 8.2-8.4 | All reconciled | Not started
8.6 | Finance sign-off | Golden Block finance signs off the opening balances | Email | Golden Block |  | 2026-11-09 |  | 8.5 | Sign-off email | Not started
8.7 | Close migration and October | Close legacy data transfer; close October posting periods | Define Settings for Legacy Data Transfer / Manage Posting Periods | SNAGFREE |  | 2026-11-10 |  | 8.6 | Closed | Not started
8.8 | Production acceptance | Golden Block confirms in writing that production works | Email | Golden Block |  | 2026-11-10 |  | 8.6 | Acceptance email | Not started
Legend
| Golden Block | Update Status, Time and Comments in the white cells. Status is a dropdown.
| SNAGFREE | Weekend in KSA is Fri-Sat: Fri 30 Oct is kept free as contingency; Sat 31 Oct is the cutover day.
| Golden Block & SNAGFREE | App names are S/4HANA Cloud Public Edition; confirm exact migration object names in Migrate Your Data in PRD.

## Sheet1
# | Activity | Owner | dependency | START Date | Due Date | Actual completion
1 | UAT SIGN OFF | ANAS | all actions starting step 2 | 2026-10-27 | 2026-10-27
1.1 | Prepare migration object on PRD | SNAGFREE |  | 2026-10-26 | 2026-10-28
2 | MM Material codes to be providded | GOLDEN BLOCK | all actions starting step 4 | 2026-10-25 | 2026-10-27
2.1 | Provide openeing balance sheets points: 10, 12,13,14,15,16) | GOLDEN BLOCK |  | 2026-10-28 | 2026-10-30
3 | 1)Confirmaiton PP & QM provided master data 2)confirm same activity types master data will be used as prd in CO 3)list of confirmed GL accounts that will be used for Company 4000 | GOLDEN BLOCK |  | 2026-10-26 | 2026-10-29
4 | Send Transport requests to Production | SNAGFREE | Step 2 | 2026-10-28 | 2026-10-28
5 | add below master data related to FICO & SD 1) Fixed assets 2) bussiness partners: ( FI supplier/customer, Customer, supplier, credit MGT) roles 3) bank accounts ( BANK KEY, house bank, account ID) 4) profit center 5) Cost center | GOLDEN BLOCK | step 4 | 2026-10-29 | 2026-10-29
6 | Upload MM Material Masterdata | SNAGFREE | Profit center in step 5 | 2026-10-31 | 2026-10-31
7 | Upload PP & QM Master data | SNAGFREE | Step 6 & Step 5 (Cost centers) | 2026-10-31 | 2026-11-01
8 | 1)maintain Activity types rates 2)RUN COST estimate for finished product | GOLDEN BLOCK | Step 7 | 2026-11-01 | 2026-11-01
9 | Create condition master data for materials ( price list for sales) - SD | GOLDEN BLOCK | Step 7 | 2026-11-01 | 2026-11-01
10 | upload opening balance MM inventory balance | SNAGFREE | STEP 2 | 2026-11-04 | 2026-11-05
11 | Review openeing balance of MM inventory with finance team | GOLDEN BLOCK | Step 10 | 2026-11-01 | 2026-11-01
12 | Upload FI/GL account bank balance | SNAGFREE | STEP 5 & 2.1 | 2026-11-02 | 2026-11-04
13 | Upload FI/GL account balances | SNAGFREE | STEP 5 & 2.1 | 2026-11-02 | 2026-11-04
14 | Upload Account payable open items | SNAGFREE | STEP 5 & 2.1 | 2026-11-02 | 2026-11-04
15 | Upload Account recivable open items | SNAGFREE | STEP 5 & 2.1 | 2026-11-02 | 2026-11-04
16 | upload fixed asset posting | SNAGFREE | STEP 5 & 2.1 | 2026-11-02 | 2026-11-04
17 | Go live - regular bussiness |  | all mentioned steps | 2026-11-05 | 2026-11-05
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214