## Plan
# | Activity | Owner | dependency | START Date | Due Date | By (time) | Actual completion | Change vs current plan
1 | UAT SIGN OFF | ANAS |  | 2026-10-27 | 2026-10-27 |  |  | Unchanged (old #1)
2 | Go-live scope signed off by Golden Block management: 1) day-1 scope = this plan 2) items moved to week 1 (sheet 'After go-live') 3) GB key users, finance and admin available Fri 30 & Sat 31 Oct | GOLDEN BLOCK (CEO/PM) + SNAGFREE | 1 | 2026-10-27 | 2026-10-28 | 12:00 |  | NEW - without this the dates below do not hold
3 | Prepare migration objects on PRD | SNAGFREE |  | 2026-10-26 | 2026-10-28 |  |  | Unchanged (old #1.1)
4 | MM material: confirm the 'Product rules' sheet - ONE row per product type (7 rows), org-level values only. No per-product sheet. Base UoM comes from the system. New UoMs / conversion factors moved to week 1. | GOLDEN BLOCK (MM / Ops) |  | 2026-10-27 | 2026-10-28 | 12:00 |  | CHANGED (old #2) - replaces the 5-day per-product preparation
5 | 1) Confirm PP & QM master data provided 2) Confirm same activity types as PRD in CO 3) List of confirmed GL accounts for company 4000 | GOLDEN BLOCK |  | 2026-10-26 | 2026-10-28 | 17:00 |  | Unchanged (old #3) - now a hard deadline
6 | Send transports to Production (SNAGFREE releases, GB admin imports in Import Collection) - incl. the White Concrete invoice form software collection | SNAGFREE + GB admin | 1 | 2026-10-28 | 2026-10-28 | 15:00 |  | Unchanged (old #4) - HARD GATE: nothing can be loaded in PRD before this
7 | Profit centers (needed by the material upload) - provide and load | GOLDEN BLOCK / SNAGFREE | 6 | 2026-10-28 | 2026-10-28 | 17:00 |  | MOVED 1 day earlier (old #5, part 4)
8 | Add master data for FICO & SD: 1) Fixed asset classes / check 2) Business partners (FI supplier/customer, customer, supplier, credit mgmt) roles 3) Bank accounts (bank key, house bank, account ID) | GOLDEN BLOCK provides / SNAGFREE loads | 6 | 2026-10-28 | 2026-10-29 | 12:00 |  | Same dates (old #5) - load right after data arrives
9 | Build the material extension file from the PRD product export + 'Product rules' (all 1,628 products; standard prices for FG/SFG taken from the Golden Block plant) | SNAGFREE (MM) | 4 | 2026-10-28 | 2026-10-28 | 20:00 |  | NEW - generated by rules, not typed per product
10 | Upload MM material master extension in PRD: simulate, load 10 products, check, then load all | SNAGFREE | 6, 7, 9 | 2026-10-29 | 2026-10-29 | 12:00 |  | MOVED from 2-3 Nov to 29 Oct (old #6)
11 | Upload PP & QM master data: work centers, BOMs, routings, production versions. QM: load what is ready; keep inspection types off for day 1 if inspection plans are not ready | SNAGFREE | 10, 5 (cost centers) | 2026-10-29 | 2026-10-30 |  |  | MOVED from 2-3 Nov (old #7)
12 | 1) Maintain activity type rates 2) Run cost estimate for finished products - or keep the standard prices from step 9 for November and cost later | GOLDEN BLOCK (CO) + SNAGFREE | 11 | 2026-10-30 | 2026-10-31 |  |  | MOVED from 3 Nov (old #8)
13 | Create condition master data for materials (sales price list) - SD | GOLDEN BLOCK + SNAGFREE (upload) | 10 | 2026-10-29 | 2026-10-31 |  |  | MOVED from 3 Nov (old #9)
14 | Business users and roles for White Concrete in PRD (restricted to company code 4000 / its plant); each key user tests login | GB admin + SNAGFREE | 6 | 2026-10-29 | 2026-10-31 |  |  | NEW - missing from current plan
15 | Smoke test in PRD: display products/BPs/prices, create and delete one sales order and one PO, preview the invoice form | SNAGFREE + GB key users | 10-14 | 2026-10-31 | 2026-10-31 | 16:00 |  | NEW
16 | Stop White Concrete postings in company code 1000; stock count at close of business; send stock sheet (qty + value) | GOLDEN BLOCK |  | 2026-10-31 | 2026-10-31 | 20:00 |  | NEW - fixes the cut-off moment
17 | GO / NO-GO call | GOLDEN BLOCK (CEO/PM) + SNAGFREE | 1-16 | 2026-10-31 | 2026-10-31 | 21:00 |  | NEW
18 | Opening balance data as of 31 Oct (steps 19, 22-26): - stock, bank, AR and AP lists: Sun 1 Nov 08:00 - provisional trial balance + fixed asset register: Sun 1 Nov 12:00 - final October figures: true-up in step 28 | GOLDEN BLOCK (Finance) | 16 | 2026-10-28 | 2026-11-01 | 08:00 / 12:00 |  | CHANGED (old #2.1, due 29 Oct) - 31 Oct balances cannot exist before 31 Oct; formats agreed 28 Oct. Note: old dependency '28-Oct-27' was a typo
19 | Upload opening balance MM inventory (movement type 561) | SNAGFREE | 10, 12, 16, 18 | 2026-11-01 | 2026-11-01 | 11:00 |  | MOVED from 4-5 Nov (old #10)
20 | Review opening balance of MM inventory with finance | GOLDEN BLOCK | 19 | 2026-11-01 | 2026-11-01 | 13:00 |  | MOVED from 4 Nov (old #11)
21 | GO-LIVE - regular business in White Concrete: - sales orders and POs from 08:00 - goods movements, production and billing after step 20 | ALL | 6-20 | 2026-11-01 | 2026-11-01 | 13:00 |  | MOVED from 5 Nov (old #17)
22 | Upload FI/GL account bank balance | SNAGFREE | 8, 18 | 2026-11-01 | 2026-11-01 |  |  | MOVED from 2-4 Nov (old #12)
23 | Upload FI/GL account balances (provisional October trial balance) | SNAGFREE | 18 | 2026-11-01 | 2026-11-02 |  |  | MOVED (old #13)
24 | Upload Account payable open items | SNAGFREE | 8, 18 | 2026-11-01 | 2026-11-02 |  |  | MOVED (old #14)
25 | Upload Account receivable open items | SNAGFREE | 8, 18 | 2026-11-01 | 2026-11-02 |  |  | MOVED (old #15)
26 | Upload fixed asset posting | SNAGFREE | 8, 18 | 2026-11-01 | 2026-11-02 |  |  | MOVED (old #16)
27 | Reconcile and sign off all opening balances = PROJECT COMPLETE | GOLDEN BLOCK (Finance) + SNAGFREE | 19-26 | 2026-11-02 | 2026-11-02 | 18:00 |  | NEW - the 2 Nov finish line
28 | October true-up postings (posting date 31 Oct) once Golden Block closes October; keep period 10 open for White Concrete until then | GOLDEN BLOCK (Finance) + SNAGFREE | 27 | 2026-11-03 |  | per GB close |  | NEW - normal after any cutover
Legend:
New step
Date moved / content changed vs current plan
Hard gate - everything after it waits
Go-live / finish line
Calendar: Fri 30 and Sat 31 Oct are weekend days - this plan needs both. Sun 1 Nov is go-live, Mon 2 Nov is the finish line. Fill 'Actual completion' as steps close.

## Product rules
Product type | Products in your export | Views to extend to the White Concrete plant | Plant | Storage location(s) | Profit center | MRP controller / production supervisor | Sales org / dist. channel / delivering plant | Price for stock load | Confirmed by / date
EXAMPLE (format only) |  | Plant/MRP, work scheduling, storage, accounting, sales | e.g. 4100 | e.g. 4101, 4102 | e.g. WC-PROD | e.g. 001 / 001 | e.g. 4000 / 10 / 4100 | Standard price from GB plant | e.g. Name, 28-Oct
Finished Product (FERT) | 391 | Plant/MRP, work scheduling, storage, accounting, sales | [5 empty] | Standard price from Golden Block plant (or cost estimate, plan step 12)
Semifinished Product (HALB) | 380 | Plant/MRP, work scheduling, storage, accounting |  |  |  |  | n/a - not sold | Standard price from Golden Block plant (or cost estimate, plan step 12)
Phantom Product (PHAN) | 711 | Plant/MRP only (phantom setting copied) - needed only if White Concrete BOMs use them |  | n/a |  |  | n/a | n/a - no stock
Raw materials (ROH) | 90 | Plant/MRP, purchasing, storage, accounting |  |  |  |  | n/a | Value in the 31 Oct stock sheet (moving average)
Packaging (VERP) | 26 | Plant/MRP, purchasing, storage, accounting |  |  |  |  | n/a | Value in the 31 Oct stock sheet (moving average)
Material general - Cons. (MAT) | 28 | Plant, purchasing, storage, accounting |  |  |  |  | n/a | Value in the 31 Oct stock sheet
Trading Goods (HAWA) | 2 | Plant/MRP, purchasing, storage, accounting, sales | [5 empty] | Value in the 31 Oct stock sheet
TOTAL | 1628
HOW TO FILL: Golden Block fills only the yellow cells - one row per product type, not per product. Row 2 shows the format.
Every other field (MRP type, lot size, procurement type, valuation class, item category group, tax classification, etc.) is copied from the same product at the Golden Block plant.
Base unit of measure already exists on every product - it is NOT typed again. New alternative units / conversion factors are moved to week 1 ('After go-live'); White Concrete sells in today's units until then.
Units of measure are product-level, shared with Golden Block - adding a unit for White Concrete also adds it for Golden Block (safe; the base unit never changes).
Per-product fine-tuning (safety stock, lot sizes, MRP controller exceptions) is done after go-live.
Product counts: from 'Product Lists FG&RM&GE&SE&SP.xlsx' (SAPUI5 export) shared by the SNAGFREE team.

## After go-live
# | Moved out of day-1 scope | Owner | Target | Why go-live is safe without it | Status
W1 | New alternative units of measure + conversion factors (only finished products sold in a new unit) | GOLDEN BLOCK list / SNAGFREE upload | 3-5 Nov | Products sell in the units Golden Block uses today | Open
W2 | Per-product MRP fine-tuning (safety stock, lot sizes) | GOLDEN BLOCK (planning) | by 12 Nov | Copied Golden Block values are a working default | Open
W3 | QM inspection plans / inspection types, if not ready by 30 Oct | GOLDEN BLOCK (QM) + SNAGFREE | by 5 Nov | Quality checks done manually in the first days; turn on inspection once plans exist | Open
W4 | White Concrete cost estimate with its own activity rates; release for 1 Dec | GOLDEN BLOCK (CO) + SNAGFREE | November | November runs on the standard prices loaded in plan step 9 | Open
W5 | October true-up postings (plan step 28) | GOLDEN BLOCK (Finance) | after GB Oct close | Posted with date 31 Oct while period 10 stays open | Open
W6 | First supplier payment run / receipts against pre-November invoices | GOLDEN BLOCK (Finance) | from 3 Nov | Needs AP/AR open items, which are complete on 2 Nov | Open
W7 | ZATCA Phase 1 QR on the invoice form (if White Concrete is B2B only) | SNAGFREE | per CR | QR is not mandated on standard (B2B) tax invoices in the generation phase | Open